## UKPN_2004
| Question No. | Proforma section | Topic | Question | Date question asked | Date response required | Date received | Follow up to Question # | Confiential (y/n) | Attachments
co | UKPN001 | Appendix G | Cost Benefit Analysis | Please explain the basis for the assumptions made in Appendix 5, section 1.1.5, regarding the proportions of the time for which the storage capacity is used for STOR, for frequency response and for specific DNO applications. | 2012-08-30 | 2012-09-04 | 2012-09-04
| UKPN002 | 2, Appendix A | Project Description, Net Benefits | In their Net benefits calculation, UKPN has subtracted the value of estimated savings accrued through displaced peak generation capacity from the method costs. Please can UKPN explain to whom these savings accrue. | 2012-08-30 | 2012-09-04 | 2012-09-04
| UKPN003 | Full Submission Workbook | Project Cost Summary | Significant expenditure is to be incurred on equipment, contractors and IT. Please provide a detailed breakdown - by work package - of what this expenditure is to be spent on including details of the equipment, services, applications etc that will be procured. | 2012-08-30 | 2012-09-04 | 2012-09-04 |  | y
| UKPN004 | Full Submission Workbook | Project Cost Summary | How have the estimated costs for equipment, contractors and IT been derived? How have you ensured that these are realistic values and that is no systematic bias in either direction? | 2012-08-30 | 2012-09-04 | 2012-09-04 |  | y
| UKPN005 | Full Submission Workbook | Project Cost Summary | Labour costs are shown as £2.533 million. Please provide the number of person days that this relates to and the resulting average cost per day per person. | 2012-08-30 | 2012-09-04 | 2012-09-04
| UKPN006 | Full Submission Workbook | Project Cost Summary | Please provide a description of how costs per person have been calculated together with a sample calculation | 2012-08-30 | 2012-09-04 | 2012-09-04
| UKPN007 | Section 2 | Project Description | Why has the proposed battery size increased from 4MW in the initial proposal to 6MW in the final submission? And what is driving the battery size requirements? | 2012-08-30 | 2012-09-04 | 2012-09-04
| UKPN008 | Section 4 | Evaluation Criteria | Please explain the degree of dependency of this project on the successful delivery of the GB Flexibility Market proposal. | 2012-08-30 | 2012-09-04 | 2012-09-04
| UKPN009 | Section 2 | Project Description | Please describe the lessons that have been learned from the previous smaller scale storage project, referred to on Page 5. | 2012-08-30 | 2012-09-04 | 2012-09-04
| UKPN010 | Section 4 | Evaluation Criteria | Please confirm that your base case is consistent with governance document assumptions (that is the Minimum Cost Scheme under which the DNO would deliver the Solution at the scale being tested within the project). Please confirm that the Base Case is delivering the same network capacity as the Method. | 2012-09-04 | 2012-09-07 | 2012-09-07
| UKPN011 | Section 2 | Project Description | How much energy will be ‘lost’ in the store and how will these losses be paid for? | 2012-09-04 | 2012-09-07 | 2012-09-07
| UKPN012 | Section 2 | Project Description | Please explain, quantitatively, how the energy and power ratings of the store have been optimised to address the future network constraint. | 2012-09-04 | 2012-09-07 | 2012-09-07
| UKPN013 | Section 2 | Project Description | Please explain why you have selected this size of battery to test the regulatory and commercial arrangements. | 2012-09-04 | 2012-09-07 | 2012-09-07
| UKPN014 | Section 6 | Project Readiness | Please outline the risks to achieving planning permission in a timely manner and the steps you have taken to mitigate these risks. | 2012-09-04 | 2012-09-07 | 2012-09-07
| UKPN015 | Section 7 | Regulatory Issues | You state that you do not expect that you will require derogation from Engineering Recommendation P2/6, but will liaise with Ofgem should this change. Please outline the likelihood of you requesting such a derogation, the likely details of the request and how you would manage the risk of such a derogation not being granted. | 2012-09-04 | 2012-09-07 | 2012-09-07
| UKPN016 | Section 3 | Project Business Case | We understand from external sources that a facility of this type is only economically viable if it is discharged daily. Your submission suggests that it will run just a few times a year. Is this realistic proposition for designing the commercial arrangements? | 2012-09-04 | 2012-09-07 | 2012-09-07
| UKPN017 | Section 4 | Evaluation Criteria | Please explain the assumptions behind the statement that 6MW storage capacity would provide annual CO2 emissions savings of 1.7kTonnes of CO2. What conversion factor for kgCO2/kWh is being assumed and for how many hours per day/year is the battery assumed to be delivering 6MW of power to offset peaking generation? | 2012-09-06 | 2012-09-11 | 2012-09-10
| UKPN018 | Section 3 Appendix G | Project Business Case Cost Benefit Analysis | Please provide the basis for the calculations quoted on p.12 of the Full Submission Pro-forma that give Future Storage Value Streams of £3.8M in revenue over 10 years and operating cost savings of £1.9M. What assumptions are being made about the value of volume of grid support services being provided and what, in detail, are the sources of the claimed "System Operation Cost Savings". | 2012-09-06 | 2012-09-10 | 2012-09-10
| UKPN019 | Appendix G | Cost Benefit Analysis | Please explain the basis for the conclusion reached that over the period 2014/15 to 2039/40 the estimate of potential GB substations at which storage could be applicable rises from 260 to 671. | 2012-09-06 | 2012-09-10 | 2012-09-10
| UKPN020 | Section 4 | Evaluation Criteria | Please provide a detailed explanation of the calculation of the cost savings estimate of £0.6bn to 2040 arising from the rollout of the SNS method across Great Britain. | 2012-09-06 | 2012-09-10 | 2012-09-10
| UKPN021 | Appendix A | Net Benefits | It is stated that the traditional reinforcement cost as the alternative to the project amounts to £8.6M. Please clarify how much of this was included in the DPCR5 settlement and how much of this cost is likely to remain in the ED1 budget request. There was a suggestion in the meeting with the Consultants that this expenditure is deferred by the project; when will it be required? | 2012-09-06 | 2012-09-10 | 2012-09-10
| UKPN022 | Section 2 | Project Description | What is the anticipated lifetime of the battery installation? | 2012-09-06 | 2012-09-10 | 2012-09-10 |  | y
| UKPN023 | Appendix A | Project Cost Summary | The costs associated with Contractors and IT in the Project Cost Summary are stated as £5.193M and £0.741M respectively. In the cost breakdown sumbmitted in reponse to question UKPN003, however, these have risen to £5.738M and £0.785M respectively. Please explain these differences and state whether this affects the overall project cost. | 2012-09-06 | 2012-09-10 | 2012-09-07 |  | y
| UKPN024 | Appendix G | Cost Benefit Analysis | Please explain the background to the calculations of income from STOR and Frequency Response in sections 1.1.4 and 1.1.5 of Appendix G, including the frequency and duration of utilisation of the batteries that is assumed, the volume of each service that is delivered, the duration over which the analysis of incomes is assessed and the assumed prices paid for the services. Please also explain to what extent it is considered likely that the project will be competitive alongside existing providers of the services. | 2012-09-06 | 2012-09-10 | 2012-09-10
| UKPN025 | Appendix G | Cost Benefit Analysis | Please provide a breakdown of the cost savings that are assumed in deriving the "once proven" deployment cost of £11.3 million for the storage solution, including a detailed breakdown of the "Innovation/1st of a kind costs" referred to in the business case. | 2012-09-20 | 2012-09-24 | 2012-09-24
| UKPN026 | Full Submission Workbook | Project Cost Summary | Please provide the average day rate for the inputs to the project from each of the project partners and contractors, together with the total number of days' input for each organisation. | 2012-09-20 | 2012-09-24 | 2012-09-24
| UKPN027 | Section 2 | Project Description | What will be the consequences of a short circuit on the battery terminals? Can the battery catch fire and with what consequences? | 2012-09-20 | 2012-09-24 | 2012-09-24
| UKPN028 | Section 2 | Project Description | Please provide a clear explanation and diagram of how the various control systems to integrate the operation of the battery with the distribution network will work without conflict. | 2012-09-20 | 2012-09-24 | 2012-09-24
| UKPN029 | Section 2 Section 3 | Project Description Business Case | Please detail the projections of the market prices and volumes that have been assumed for STOR and Frequency Response services in the future and the assumed comparison between the prices at which these services can be offered by the SNS project and other service providers. | 2012-09-20 | 2012-09-24 | 2012-09-24
| UKPN030 | Section 2 | Project Description | We understand that the battery and power converter are modular (2MW/5MWh per module). What is the cost of a 4MW/10MWh battery compared to the proposed 6MW/15MWh battery? To what extent could you leave provision for the installation for an additional module in future? Why can you not use the existing UKPN battery to gain learning on commercial arrangements? | 2012-09-27 | 2012-10-02 | 2012-10-02 |  | y
| UKPN031 | Section 2 | Project Description | What additional learning will result from this project over and above that from other committed LCN Fund projects involving batteries? Specifically, what additional commercial or other learning will this project generate compared to Customer Led Network Revolution? | 2012-09-27 | 2012-10-02 | 2012-10-02
| UKPN032 | Section 2 | Project Description | What is the operating strategy for the battery? How do you plan to prioritise its different uses? | 2012-09-27 | 2012-10-02 | 2012-10-02
| UKPN033 | Section 3 | Project Business Case | What conditions might be necessary for this Method to become commercially viable and how likely are they? | 2012-09-27 | 2012-10-02 | 2012-10-02
| UKPN034 | Section 3 | Project Business Case | Please confirm the network capacity increase provided by the Base Case. | 2012-09-27 | 2012-10-02 | 2012-10-02
| UKPN035 | Section 8 | Customer Impacts | You have highlighted that there is an increased risk in unplanned interruptions due to fault outages. As required by the governance document, please indicate the potential number and duration of these unplanned interruptions. | 2012-10-02 | 2012-10-04 | 2012-10-04
| UKPN036 | Section 3 | Project Business Case | Please provide estimates of the current market size for STOR and frequency response, and projections for the market size for STOR and frequency response up to 2030. | 2012-10-02 | 2012-10-04 | 2012-10-04
|  | Full Submission Workbook | Project Costs | Following your resubmission, please provide the updated average day rate for the inputs to the project from each of the project partners and contractors, together with the total number of days' input for each organisation | 2012-10-16 | 2012-10-18 | 2012-10-18
| UKPN039 | Full Submission Workbook Section 6 | Project Costs Project Readiness | We note your first choice battery supplier, A123 systems, has entered Chapter 11 bankruptcy. Please explain how this will impact your approach to the project and any potential changes to costs. | 2012-10-23 | 2012-10-25 | 2012-10-25