## SSE_2004
| Question No. | Proforma section | Topic | Question | Date question asked | Date response required | Date received | Follow up to Question # | Confiential (y/n) | Attachments
co | SSEP001 | 5 | Knowledge Dissemination | Please explain how does SHEPD proposes to engage with stakeholders, in terms of gathering their views on the proposals as they develop. | 2012-08-30 | 2012-09-03 | 2012-09-03
| SSEP002 | 2 | Project Description | Reference is made to the use of an Active Network Management (ANM) system in the various phases of the project. Please provide more details of this and describe the state of readiness of this system and its applicability to optimising the loading of an electrolyser. | 2012-08-30 | 2012-09-04 | 2012-09-03
| SSEP003 | 2 | Project Description | Given the additional technical and commercial complexity of using a hydrogen electrolyser to facilitate a wind development, how has SSE assured themselves that there will be sufficient demand for this solution? And given the sample size of generators in the project trial is small, how will demand for the solution be tested during the project? | 2012-08-30 | 2012-09-04 | 2012-09-04 |  | y
| SSEP004 | 3 | Project Business Case | Please explain the basis for the statement that electrolyser operation could be commercially viable by 2020 | 2012-08-30 | 2012-09-03 | 2012-09-03 |  | y
| SSEP005 | Appendix C(ii) | Risk Register | Please explain how the risks to the project of obtaining planning permission for significant items of equipment have been addressed. | 2012-08-30 | 2012-09-04 | 2012-09-03
| SSEP006 | 2 | Project Description | If the hydrogen electrolyser is acting as a flexible demand for renewable generation, how has the reliability of hydrogen electrolysers been considered in the project design? | 2012-08-30 | 2012-09-04 | 2012-09-04 |  | y
| SSEP007 | Appendix C(i) | Project Plan | The project plan contains a large number of long duration activities with no indication of subtasks or the interactions/dependencies between tasks. Please provide more detailed information as to the definition, timing and interactions between project subtasks. | 2012-08-30 | 2012-09-04 | 2012-09-03 |  | y
| SSEP008 | Full Submission Workbook | Project Cost Summary | Significant expenditure is to be incurred on equipment, contractors and IT. Please provide a detailed breakdown - by work package - of what this expenditure is to be spent on including details of the equipment, services, applications etc that will be procured. | 2012-09-04 | 2012-09-07 | 2012-09-07 |  | y
| SSEP009 | Full Submission Workbook | Project Cost Summary | How have the estimated costs for equipment, contractors and IT been derived? How have you ensured that these are realistic values and that is no systematic bias in either direction? | 2012-09-04 | 2012-09-07 | 2012-09-07 |  | y
| SSEP010 | Full Submission Workbook | Project Cost Summary | Labour costs are shown as £5.331 million. Please provide the number of person days that this relates to and the resulting average cost per day per person. | 2012-09-04 | 2012-09-07 | 2012-09-07 |  | y
| SSEP011 | Full Submission Workbook | Project Cost Summary | Please provide a description of how costs per person have been calculated together with a sample calculation. | 2012-09-04 | 2012-09-07 | 2012-09-07 |  | y
| SSEP012 | 2 | Project Description | In Phase 2, the electrolysers are only adding 3MW of demand. Please explain in detail how this additional load allows 60MW of generation to be connected at Bridge of Don substation (i.e. what constraints does it address and how?). | 2012-09-04 | 2012-09-07 | 2012-09-07 |  | y
| SSEP013 | 2 | Project Description | Have detailed studies, including fault level assessment, been carried out to confirm the viability of the connection of the 60MW wind farm, recognising that the electrolyser load will not be continuous? | 2012-09-04 | 2012-09-07 | 2012-09-07 |  | y
| SSEP014 | 2 | Project Description | The proposal states (page 9) that other network management options are available to allow the wind farm to connect if the electrolysers are not connected. What are these options? | 2012-09-04 | 2012-09-07 | 2012-09-07 |  | y
| SSEP015 | 3 | Project Business Case | Please outline the benefits that will flow to gas customers | 2012-09-04 | 2012-09-07 | 2012-09-07 |  | y
| SSEP016 | 7 | Regulatory Issues | You state that you may require derogation from Engineering Recommendation P2/6. Please outline the likelihood of you requesting such a derogation, the likely details of the request and how you would manage the risk of such a derogation not being granted. | 2012-09-04 | 2012-09-08 | 2012-09-07
| SSEP017 | Section 3 | Business Case | In respect of the European Offshore Wind Deployment Centre (EOWDC) please provide the estimated connection charge payable by Vattenfall in each of the following two cases:- (1) where a traditional 132kV connection is made and (2) where a connection is made at 33 kV associated with an active network management scheme and hydrogen production facilities | 2012-09-06 | 2012-09-10 | 2012-09-10 |  | y
| SSEP018 | Section 3 | Business Case | At the meeting between the PATHS project team and Ofgem’s consultants on 4th September it was stated that it was expected that the cost of hydrogen produced by electrolysis in 2020 would be one and a half to twice the cost of that produced by conventional means. Please can you confirm that this is the expected difference in hydrogen production costs. | 2012-09-06 | 2012-09-10 | 2012-09-10
| SSEP019 | Full Submission Workbook | Project Cost Summary | Please provide the average day rate for the inputs to the project from each of the project partners and contractors, together with the total number of days' input for each organisation. | 2012-09-20 | 2012-09-24 | 2012-09-24 |  | y
| SSEP020 | Section 3 | Business Case | What fraction of the hydrogen demand for the 10 buses will be supplied by the 1MW wind turbine? | 2012-09-20 | 2012-09-24 | 2012-09-24 |  | y
| SSEP021 | Section 2 | Project Description | Please provide details of whether the proposed electrolyser technology has been built and demonstrated in other projects nationally or internationally. | 2012-09-20 | 2014-09-24 | 2012-09-24 |  | y
| SSEP022 | Section 2 | Project Description | Please provide confirmation that there are no significant safety or quality issues associated with introducing hydrogen into the gas grid at the levels proposed in the project. | 2012-09-20 | 2014-09-24 | 2012-09-24 |  | y
| SSEP023 | Section 3 | Business Case | What are the other technical solutions to connect the wind farm and what do they cost? What proportion of these costs would be met by the connectee? | 2012-09-27 | 2012-10-02 | 2012-10-02 |  | y
| SSEP024 | Section 2 | Project Description | Please explain the role of the ANM scheme in this project. | 2012-09-27 | 2012-10-02 | 2012-10-02
| SSEP025 | Section 3 | Business Case | Are you assuming that hydrogen will only be produced by excess wind, or will it also be produced at other times, eg in off-peak periods? | 2012-09-27 | 2012-10-02 | 2012-10-02 |  | y
| SSEP026 | Section 3 | Business Case | Can the wind farm connect to the transmission system and, if so, will the transmission connection offer a firm connection? | 2012-09-27 | 2012-10-02 | 2012-10-02 |  | y
| SSEP027 | Section 3 | Business Case | SNG’s contribution is “subject to further application”. Please clarify the expected source of SNG’s contribution to the project. | 2012-09-27 | 2012-10-02 | 2012-10-02
| SSEP028 | Section 3 | Business Case | What is the status of discussions with Vattenfall over connection to the 33kV network? What mitigations are in place if Vattenfall chooses an alternative connection or the project does not progress. | 2012-09-27 | 2012-10-02 | 2012-10-02 |  | y
| SSEP029 | Section 2 | Project Description | Please confirm exactly what benefits you expect will be provided directly to electricity distribution customers? | 2012-09-27 | 2012-10-02 | 2012-10-02 |  | y
| SSEP030 | Section 2 | Project Description | Could the project boundary be redefined so that SSE provides the ANM connection but not the electrolysers? | 2012-09-27 | 2012-10-02 | 2012-10-02
| SSEP031 | Full Submission Workbook | Project Costs | Following your resubmission, please provide the updated average day rate for the inputs to the project from each of the project partners and contractors, together with the total number of days' input for each organisation | 2012-10-16 | 2012-10-18 | 2012-10-18